## Sheet1
MaintActivityType | Maintenance Plan | Maintenance item | Group | Group Counter | Required by | Basic start date | Revision | Order | Functional Location | Sort field | Description of functional location | Description | Main work center | Planner group | User Status | System status | Order Type | Room | Total planned costs | Total actual costs | Budget Line | Notification
300 | 479294 | 2012241 | 5008035 | 1 | 2016-09-28 | 2016-11-17 | Y16WK46 | 12772812 | 10050BN267 | 267HO004 | Bin, Headframe Surge | Surge Bin Radiation Elec Test | TEMUEL | 02E | RSHD ASMD | REL PRT NMAT PRC SETC | ZPM3 | 02ED1 | 221.54 | 0 | 30012770
200 | [5 empty] | 2016-08-28 |  | 12786658 | 10050BN267 | 267HO004 | Bin, Headframe Surge | repair conduit | TEMUEL | 02E | APRD | TECO PCNF ESTC NMAT PRC SETC | ZPM2 |  | 110.77 | 332.31 | 30012768 | 11083484
200 | [5 empty] | 2016-08-14 |  | 12769563 | 10050BN267 | 267HO004 | Bin, Headframe Surge | Pre charge accumulater scrolls | TEMUME | 02M | APRD | CLSD PCNF ESTC NMAT PRC SETC | ZPM2 |  | 217.46 | 217.46 | 30012769 | 11075243
300 | 479294 | 2012241 | 5008035 | 1 | 2016-03-30 | 2016-06-29 | Y16WK25 | 12552104 | 10050BN267 | 267HO004 | Bin, Headframe Surge | Surge Bin Radiation Elec Test | TEMUEL | 02E | RSCH STPD | TECO PRT NMAT PRC SETC | ZPM3 | 02ED7 | 256 | 0 | 30012770
300 | 479294 | 2012241 | 5008035 | 1 | 2016-06-29 | 2016-06-29 | Y16WK25 | 12663832 | 10050BN267 | 267HO004 | Bin, Headframe Surge | Surge Bin Radiation Elec Test | TEMUEL | 02E | RSCH ASMD STPD | TECO PRT MOBI NMAT PRC SETC | ZPM3 | 02ED7 | 133 | 0 | 30012770
200 | [5 empty] | 2016-02-13 |  | 12547601 | 10050BN267 | 267HO004 | Bin, Headframe Surge | install plathform over surge bin | TEMUME | 02M | APRD | CLSD PCNF ESTC NMAT PRC SETC | ZPM2 |  | 0 | 1823.5 | 30012769 | 10956078
300 | 479294 | 2012241 | 5008035 | 1 | 2015-12-30 | 2015-12-30 | Y15WK52 | 12437416 | 10050BN267 | 267HO004 | Bin, Headframe Surge | Surge Bin Radiation Elec Test | TEMUEL | 02E | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 02ED7 | 105 | 133 | 30012770
100 |  |  |  |  | 2015-12-01 | 2015-12-29 |  | 12358023 | 10050BN267 | 267HO004 | Bin, Headframe Surge | Surface surge bin wall needs new liners | TEMUME | 02M | PLND | CLSD PCNF ESTC GMPS MACM PPRT PRC SETC | ZPM1 | WFP | 21197.83 | 20379.87 | 30012769 | 10858967
100 |  |  |  |  | 2015-12-29 | 2015-12-29 | Y15WK52 | 12457892 | 10050BN267 | 267HO004 | Bin, Headframe Surge | Weld repairs in surge bin | TEMUME | 02M | SCHD | TECO PRT NMAT PRC SETC | ZPM1 | 02MD6 | 3120 | 0 | 30012769 | 10909527
100 |  |  |  |  | 2015-08-16 | 2015-11-11 | Y15WK45 | 12327575 | 10050BN267 | 267HO004 | Bin, Headframe Surge | Very top lighting not working on headfra | TEMUEL | 02E | SCHD | CLSD PRT NMAT PRC SETC | ZPM1 | 02ED7 | 1155 | 0 | 30012768 | 10839212
200 | [5 empty] | 2015-11-10 |  | 12404626 | 10050BN267 | 267HO004 | Bin, Headframe Surge | Repairs to Danger Sign on the stairway. | TEMUME | 02M | APRD | CLSD PCNF ESTC NMAT PRC SETC | ZPM2 |  | 150 | 150 | 30012769 | 10883781
300 | 479294 | 2012241 | 5008035 | 1 | 2015-09-30 | 2015-10-31 | Y15WK44 | 12321709 | 10050BN267 | 267HO004 | Bin, Headframe Surge | Surge Bin Radiation Elec Test | TEMUEL | 02E | SCHD STPD | CLSD PRT NMAT PRC SETC | ZPM3 | 02ED3 | 210 | 0 | 30012770
200 | [5 empty] | 2015-09-25 |  | 12370979 | 10050BN267 | 267HO004 | Bin, Headframe Surge | pre-Fab and Install Safety Gate. | TEMUME | 02M | APRD | CLSD PCNF ESTC NMAT PRC SETC | ZPM2 |  | 900 | 900 | 30012769 | 10865900
100 |  |  |  |  | 2015-10-01 | 2015-09-15 |  | 12355049 | 10050BN267 | 267HO004 | Bin, Headframe Surge | Repair surge bin wall | TEMUME | 02M | SCHD | TECO PCNF ESTC GMPS MSPT PPRT PRC SETC | ZPM1 |  | 8668.17 | 5035.36 | 30012769 | 10857616
300 | 479294 | 2012241 | 5008035 | 1 | 2015-07-01 | 2015-07-01 | Y15WK27 | 12206085 | 10050BN267 | 267HO004 | Bin, Headframe Surge | Surge Bin Radiation Elec Test | TEMUEL | 02E | STPD | CLSD PRT NMAT PRC SETC | ZPM3 | 02ED3 | 105 | 0 | 30012770
100 |  |  |  |  | 2015-05-17 | 2015-05-12 | Y15WK20 | 12192401 | 10050BN267 | 267HO004 | Bin, Headframe Surge | Repairs to surface surge bin | TEMUME | 02M | SCHD | CLSD PCNF ESTC GMPS PPRT PRC SETC | ZPM1 | 02ED2 | 2274.55 | 2200 | 30012769 | 10776281
200 | [5 empty] | 2015-05-04 |  | 12186014 | 10050BN267 | 267HO004 | Bin, Headframe Surge | install uni struts for electricians | TEMUME | 02M | APRD | CLSD PCNF ESTC NMAT PRC SETC | ZPM2 |  | 100 | 200 |  | 10773057
300 | 479294 | 2012241 | 5008035 | 1 | 2015-04-01 | 2015-04-01 | Y15WK14 | 12086262 | 10050BN267 | 267HO004 | Bin, Headframe Surge | Surge Bin Radiation Elec Test | TEMUEL | 02E | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 02ED3 | 210 | 105 | 30012770
100 |  |  |  |  | 2015-01-27 | 2015-01-27 | Y15WK05 | 12052740 | 10050BN267 | 267HO004 | Bin, Headframe Surge | Repair hole in surface bin | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM1 | 02MD2 | 2200 | 2600 | 30012769 | 10712275
200 |  |  |  |  | 2015-01-22 | 2015-01-22 |  | 12050299 | 10050BN267 | 267HO004 | Bin, Headframe Surge | Surge bins HAWK sensor level fault | TEMUEL | 02E | APRD | CLSD PCNF ESTC NMAT PRC SETC | ZPM2 |  | 525 | 525 |  | 10710908
100 |  |  |  |  | 2014-12-04 | 2015-01-20 | UGSD0115 | 11952815 | 10050BN267 | 267HO004 | Bin, Headframe Surge | Repair Worn Areas of Surge Bin | TEMUME | 02S | SCHD | CLSD PCNF ESTC GMPS MSPT PPRT PRC SETC | ZPM1 | 02MD2 | 29511.63 | 37982.74 | 30012769 | 10665796
300 | 479294 | 2012241 | 5008035 | 1 | 2014-12-31 | 2015-01-19 | Y15WK04 | 11963938 | 10050BN267 | 267HO004 | Bin, Headframe Surge | Surge Bin Radiation Elec Test | TEMUEL | 02E | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 02ED1 | 105 | 105 | 30012770
100 |  |  |  |  | 2014-11-18 | 2014-11-18 | Y14WK47 | 11953802 | 10050BN267 | 267HO004 | Bin, Headframe Surge | Replace wear plates in the surge bin | TEMUME | 02M | SCHD | CLSD PCNF ESTC GMPS MACM PPRT PRC SETC | ZPM1 | 2UGM | 3690.37 | 5225.37 | 30012769 | 10666101
100 |  |  |  |  | 2014-08-31 | 2014-10-28 | Y14WK44 | 11779836 | 10050BN267 | 267HO004 | Bin, Headframe Surge | Replace Lip Liners In Surge Bin | TEMUME | 02M | SCHD | CLSD PCNF ESTC GMPS MACM PPRT PRC SETC | ZPM1 | 2UGM | 29451.42 | 29643.35 | 30000017 | 10597801
300 | 479294 | 2012241 | 5008035 | 1 | 2014-10-01 | 2014-10-01 | Y14WK40 | 11835962 | 10050BN267 | 267HO004 | Bin, Headframe Surge | Surge Bin Radiation Elec Test | TEMUEL | 02E | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | UGE3 | 210 | 105 | 30012770
210 |  |  |  |  | 2014-09-18 | 2014-09-17 |  | 11877533 | 10050BN267 | 267HO004 | Bin, Headframe Surge | grease lines | TEMUME | 02M | APRD | CLSD PCNF ESTC GMPS MACM PRC SETC | ZPM2 |  | 165.4 | 215.4 | 30000017 | 10629927
200 | [5 empty] | 2014-09-10 |  | 11867410 | 10050BN267 | 267HO004 | Bin, Headframe Surge | Replace Lights At Sheave Wheel level | TEMUEL | 02E | APRD | CLSD PCNF ESTC GMPS MACM PRC SETC | ZPM2 |  | 2510.09 | 2090.09 | 30012768 | 10625826
200 |  |  |  |  | 2014-09-04 | 2014-09-04 |  | 11858805 | 10050BN267 | 267HO004 | Bin, Headframe Surge | Hawk bin sensor trip | TEMUEL | 02E | APRD | CLSD PCNF ESTC NMAT PRC SETC | ZPM2 |  | 210 | 210 | 30000016 | 10622234
310 | 438639 | 2044814 | 5019107 | 1 | 2014-07-15 | 2014-07-21 | Y14WK30 | 11705759 | 10050BN267 | 267 | Bin, Headframe Surge | Inspection Of SALA Blocks | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 200 | 100 | 30003897
100 |  |  |  |  | 2014-07-19 | 2014-07-19 | Y14WK29 | 11757264 | 10050BN267 | 267HO004 | Bin, Headframe Surge | Install new anaconda for HAWK level sens | TEMUEL | 02E | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM1 | 6UGE | 315 | 315 | 30000016 | 10590376
310 | 426373 | 2031352 | 5023350 | 1 | 2014-07-15 | 2014-07-16 | Y14WK29 | 11705742 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PRT NMAT PRC SETC | ZPM3 | 3UGM | 150 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2014-07-08 | 2014-07-12 | Y14WK28 | 11696014 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PRT NMAT PRC SETC | ZPM3 | 6UGM | 150 | 0 | 30003897
200 | [5 empty] | 2014-07-04 |  | 11753022 | 10050BN267 | 267HO004 | Bin, Headframe Surge | Replace HAWK transducer | TEMUEL | 02E | APRD | CLSD ESTC GMPS MACM PRC SETC | ZPM2 |  | 2438.75 | 2438.75 | 30012768 | 10589054
310 | 426373 | 2031352 | 5023350 | 1 | 2014-07-01 | 2014-07-01 | Y14WK27 | 11686347 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PRT CSER NMAT PRC SETC | ZPM3 | 2UGM | 0 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2014-06-24 | 2014-06-28 | Y14WK26 | 11676228 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PRT NMAT PRC SETC | ZPM3 | 6UGM | 115.5 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2014-06-17 | 2014-06-17 | Y14WK25 | 11666349 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 115.5 | 115.5 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2014-06-10 | 2014-06-10 | Y14WK24 | 11655758 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 115.5 | 154 | 30003897
200 | [5 empty] | 2014-06-09 |  | 11713747 | 10050BN267 | 267 | Bin, Headframe Surge | fabricate pipe clamp | TEMUME | 02M | APRD | CLSD PCNF ESTC GMPS MACM PRC SETC | ZPM2 |  | 32.55 | 494.55 | 30003899 | 10575216
310 | 426373 | 2031352 | 5023350 | 1 | 2014-06-03 | 2014-06-03 | Y14WK23 | 11645931 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 115.5 | 115.5 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2014-05-27 | 2014-05-31 | Y14WK22 | 11636319 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 6UGM | 115.5 | 231 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2014-05-20 | 2014-05-20 | Y14WK21 | 11626474 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 115.5 | 231 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2014-05-13 | 2014-05-13 | Y14WK20 | 11616345 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 115.5 | 115.5 | 30003897
310 | 438639 | 2044814 | 5019107 | 1 | 2014-04-15 | 2014-05-06 | Y14WK19 | 11576352 | 10050BN267 | 267 | Bin, Headframe Surge | Inspection Of SALA Blocks | TEMUME | 02M | SCHD | CLSD PRT NMAT PRC SETC | ZPM3 | 2UGM | 154 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2014-05-06 | 2014-05-06 | Y14WK19 | 11605819 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 115.5 | 77 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2014-04-29 | 2014-04-29 | Y14WK18 | 11596100 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 115.5 | 115.5 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2014-04-22 | 2014-04-22 | Y14WK17 | 11586185 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 115.5 | 77 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2014-04-15 | 2014-04-20 | Y14WK16 | 11576327 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 7UGM | 115.5 | 77 | 30003897
200 | [5 empty] | 2014-04-14 |  | 11634785 | 10050BN267 | 267 | Bin, Headframe Surge | remove ecam | TEMUME | 02M | APRD | CLSD ESTC NMAT PRC SETC | ZPM2 |  | 0 | 0 |  | 10545399
310 | 426373 | 2031352 | 5023350 | 1 | 2014-04-08 | 2014-04-08 |  | 11566535 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | PLND | CLSD NCMP NMAT PRC | ZPM3 |  | 115.5 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2014-04-01 | 2014-04-05 | Y14WK14 | 11556835 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PRT NMAT PRC SETC | ZPM3 | 6UGM | 115.5 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2014-03-25 | 2014-03-25 | Y14WK13 | 11545859 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PRT NMAT PRC SETC | ZPM3 | 2UGM | 231 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2014-03-18 | 2014-03-22 | Y14WK12 | 11536295 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 6UGM | 231 | 306 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2014-03-11 | 2014-03-11 | Y14WK11 | 11526621 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 231 | 154 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2014-03-04 | 2014-03-08 | Y14WK10 | 11516575 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 6UGM | 231 | 77 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2014-02-25 | 2014-02-25 | Y14WK09 | 11507771 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 231 | 77 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2014-02-18 | 2014-02-22 | Y14WK08 | 11496795 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 6UGM | 231 | 77 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2014-02-11 | 2014-02-11 | Y14WK07 | 11487170 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PRT NMAT PRC SETC | ZPM3 | 2UGM | 231 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2014-02-04 | 2014-02-08 | Y14WK06 | 11477770 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 6UGM | 231 | 154 | 30003897
200 | [5 empty] | 2014-02-01 |  | 11532313 | 10050BN267 | 267 | Bin, Headframe Surge | repair headframe lighting | TEMUEL | 02E | APRD | CLSD PCNF ESTC NMAT PRC SETC | ZPM2 |  | 0 | 316 | 30003858 | 10508015
310 | 426373 | 2031352 | 5023350 | 1 | 2014-01-28 | 2014-01-28 | Y14WK05 | 11467373 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 02M2 | 231 | 385 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2014-01-21 | 2014-01-22 | Y14WK04 | 11457231 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 3UGM | 231 | 77 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2014-01-14 | 2014-01-14 | Y14WK03 | 11447757 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 231 | 77 | 30003897
310 | 438639 | 2044814 | 5019107 | 1 | 2014-01-14 | 2014-01-13 | Y14WK03 | 11447782 | 10050BN267 | 267 | Bin, Headframe Surge | Inspection Of SALA Blocks | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 1UGM | 924 | 77 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2014-01-07 | 2014-01-07 | Y14WK02 | 11436379 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PRT NMAT PRC SETC | ZPM3 | 2UGM | 231 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-12-31 | 2013-12-31 | Y14WK01 | 11426838 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 231 | 462 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-12-24 | 2013-12-25 | Y13WK52 | 11416404 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PRT NMAT PRC SETC | ZPM3 | 3UGM | 77 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-12-17 | 2013-12-17 | Y13WK51 | 11397029 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PRT NMAT PRC SETC | ZPM3 | 2UGM | 231 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-12-10 | 2013-12-10 | Y13WK50 | 11386411 | 10050BN267 | 267 | Bin, Headframe Surge | Skip Discharge Bin Weekly Running Insp | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 77 | 77 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-12-03 | 2013-12-03 | Y13WK49 | 11375785 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PRT NMAT PRC SETC | ZPM3 | 2UGM | 231 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-11-26 | 2013-11-30 | Y13WK48 | 11365498 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 6UGM | 231 | 231 | 30003897
200 | [5 empty] | 2013-11-25 |  | 11435607 | 10050BN267 | 267 | Bin, Headframe Surge | Check skip overwind switch | TEMUME | 02M | APRD | CLSD PCNF ESTC NMAT PRC SETC | ZPM2 |  | 0 | 237 |  | 10473395
200 | [5 empty] | 2013-11-25 |  | 11435609 | 10050BN267 | 267 | Bin, Headframe Surge | Mount 2 possy box on rope inspection dec | TEMUME | 02M | APRD | CLSD PCNF ESTC NMAT PRC SETC | ZPM2 |  | 0 | 158 |  | 10473397
310 | 426373 | 2031352 | 5023350 | 1 | 2013-11-19 | 2013-11-19 | Y13WK47 | 11350314 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 231 | 385 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-11-12 | 2013-11-12 |  | 11339817 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | PLND | CLSD NCMP NMAT PRC | ZPM3 |  | 231 | 0 | 30003897
200 | [5 empty] | 2013-11-08 |  | 11410501 | 10050BN267 | 267 | Bin, Headframe Surge | replace light sw rope inspection plat | TEMUEL | 02E | APRD | CLSD ESTC GMPS MACM PRC SETC | ZPM2 |  | 876.2 | 759.69 | 30003858 | 10464599
310 | 426373 | 2031352 | 5023350 | 1 | 2013-11-05 | 2013-11-05 | Y13WK45 | 11324403 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 231 | 308 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-10-29 | 2013-11-02 | Y13WK44 | 11313753 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 6UGM | 231 | 231 | 30003897
200 | [5 empty] | 2013-10-27 |  | 11383206 | 10050BN267 | 267 | Bin, Headframe Surge | c/o light sw rope inspect platform | TEMUEL | 02E | APRD | CLSD PCNF ESTC GMPS MACM PRC SETC | ZPM2 |  | 167.29 | 483.29 | 30003858 | 10458537
310 | 426373 | 2031352 | 5023350 | 1 | 2013-10-22 | 2013-10-22 | Y13WK43 | 11303399 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 231 | 77 | 30003897
310 | 438639 | 2044814 | 5019107 | 1 | 2013-10-15 | 2013-10-19 | Y13WK42 | 11277698 | 10050BN267 | 267 | Bin, Headframe Surge | Inspection Of SALA Blocks | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 6UGM | 616 | 77 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-10-15 | 2013-10-15 | Y13WK42 | 11277678 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 231 | 154 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-10-08 | 2013-10-08 | Y13WK41 | 11267206 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 231 | 154 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-10-01 | 2013-10-01 | Y13WK40 | 11257278 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PRT NMAT PRC SETC | ZPM3 | 2UGM | 231 | 0 | 30003897
200 | [5 empty] | 2013-10-01 |  | 11340045 | 10050BN267 | 267 | Bin, Headframe Surge | Repair loose cable tray cover. | TEMUME | 02M | APRD | CLSD PCNF ESTC NMAT PRC SETC | ZPM2 |  | 0 | 158 |  | 10444549
310 | 426373 | 2031352 | 5023350 | 1 | 2013-09-24 | 2013-09-24 | Y13WK39 | 11243428 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 216 | 72 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-09-17 | 2013-09-17 |  | 11232836 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | PLND | CLSD NCMP NMAT PRC | ZPM3 |  | 216 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-09-10 | 2013-09-10 |  | 11223723 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | PLND | CLSD NCMP NMAT PRC | ZPM3 |  | 216 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-09-03 | 2013-09-03 |  | 11209403 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | PLND | CLSD NCMP NMAT PRC | ZPM3 |  | 216 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-08-27 | 2013-08-27 |  | 11199099 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | PLND | CLSD NCMP NMAT PRC | ZPM3 |  | 216 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-08-20 | 2013-08-20 |  | 11188740 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | PLND | CLSD NCMP NMAT PRC | ZPM3 |  | 216 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-08-13 | 2013-08-13 |  | 11178439 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | PLND | CLSD NCMP NMAT PRC | ZPM3 |  | 216 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-08-06 | 2013-08-06 |  | 11167879 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | PLND | CLSD NCMP NMAT PRC | ZPM3 |  | 216 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-07-30 | 2013-07-30 |  | 11156542 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | PLND | CLSD NCMP NMAT PRC | ZPM3 |  | 216 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-07-23 | 2013-07-23 | Y13WK30 | 11144350 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PRT NMAT PRC SETC | ZPM3 | 2UGM | 216 | 0 | 30003897
310 | 438639 | 2044814 | 5019107 | 1 | 2013-04-16 | 2013-07-22 |  | 10981798 | 10050BN267 | 267 | Bin, Headframe Surge | Inspection Of SALA Blocks | TEMUME | 02M | SCHD | CLSD PRT NMAT PRC SETC | ZPM3 |  | 0 | 0 | 30003897
310 | 438639 | 2044814 | 5019107 | 1 | 2013-07-16 | 2013-07-22 | Y13WK29 | 11133639 | 10050BN267 | 267 | Bin, Headframe Surge | Inspection Of SALA Blocks | TEMUME | 02M | SCHD | CLSD PRT NMAT PRC SETC | ZPM3 | 2UM | 576 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-07-16 | 2013-07-16 | Y13WK29 | 11133625 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UM | 216 | 288 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-07-09 | 2013-07-09 | Y13WK28 | 11116642 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 144 | 72 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-07-02 | 2013-07-06 | Y13WK27 | 11104043 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD NMAT PRC SETC | ZPM3 | 2UM | 216 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-06-25 | 2013-06-25 | Y13WK26 | 11093976 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UM | 210 | 210 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-06-11 | 2013-06-18 | Y13WK24 | 11071702 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 5UM | 210 | 70 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-06-18 | 2013-06-18 | Y13WK25 | 11081569 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 210 | 70 | 30003897
200 |  |  |  |  | 2013-06-08 | 2013-06-08 |  | 11139594 | 10050BN267 | 267 | Bin, Headframe Surge | Replace faulty VEGA sensor at Winder | TEMUEL | 02M | APRD | CLSD PCNF ESTC CSER GMPS MACM PRC SETC | ZPM2 |  | 350 | 350 | 30000017 | 10384481
310 | 426373 | 2031352 | 5023350 | 1 | 2013-06-04 | 2013-06-04 | Y13WK23 | 11063000 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 210 | 140 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-05-28 | 2013-05-29 | Y13WK22 | 11051329 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 02M3 | 210 | 490 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-05-21 | 2013-05-21 | Y13WK21 | 11036871 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PRT NMAT PRC SETC | ZPM3 | 2UGM | 210 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-05-14 | 2013-05-14 | Y13WK20 | 11028696 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 210 | 70 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-05-07 | 2013-05-07 | Y13WK19 | 11020530 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 210 | 210 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-04-30 | 2013-05-01 | Y13WK18 | 11009497 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 3UGM | 210 | 140 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-04-23 | 2013-04-23 | Y13WK17 | 10997544 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 210 | 210 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-04-16 | 2013-04-16 | Y13WK16 | 10981780 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 140 | 70 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-04-09 | 2013-04-09 | Y13WK15 | 10967250 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 210 | 70 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-04-02 | 2013-04-02 | Y13WK14 | 10960224 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 210 | 70 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-03-26 | 2013-03-26 | Y13WK13 | 10953652 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 210 | 140 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-03-19 | 2013-03-20 | Y13WK12 | 10946707 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 3UGM | 210 | 70 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-03-12 | 2013-03-16 | Y13WK11 | 10940212 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 210 | 280 | 30003897
100 |  |  |  |  | 2012-04-30 | 2013-03-11 |  | 10637071 | 10050BN267 | 267 | Bin, Headframe Surge | Change out large liner plates in Bin | TEMUME | 02M | PLND | CLSD ESTC GMPS MACM PRC SETC | ZPM1 |  | 17212.96 | 14892 | 30003899 | 10196036
310 | 426373 | 2031352 | 5023350 | 1 | 2013-03-05 | 2013-03-06 | Y13WK10 | 10933449 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 3UGM | 210 | 70 | 30003897
100 |  |  |  |  | 2013-03-10 | 2013-03-04 |  | 10980959 | 10050BN267 | 267 | Bin, Headframe Surge | Change out plates | TEMUME | 02M | SCHD | CLSD PCNF ESTC GMPS MSPT PPRT PRC SETC | ZPM1 |  | 3969.92 | 3441.95 | 30003898 | 10332698
310 | 426373 | 2031352 | 5023350 | 1 | 2013-02-26 | 2013-02-28 | Y13WK09 | 10926459 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 3UGM | 210 | 490 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-02-19 | 2013-02-22 | Y13WK08 | 10919770 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF GMPS MSPT PPRT PRC SETC | ZPM3 | 5UGM | 238.8 | 238.8 | 30003897
300 | 418852 | 2021587 | 5019107 | 1 | 2013-01-07 | 2013-02-18 |  | 10879031 | 10050BN267 | 267 | Bin, Headframe Surge | Annual Inspection Of SALA Blocks | TEMUME | 02M | PLND | CLSD NCMP NMAT PRC | ZPM3 |  | 6720 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-02-12 | 2013-02-12 | Y13WK07 | 10912851 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 210 | 280 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-02-05 | 2013-02-07 | Y13WK06 | 10906456 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 4UGM | 210 | 210 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-01-29 | 2013-01-29 | Y13WK05 | 10899959 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 210 | 210 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-01-22 | 2013-01-22 |  | 10893357 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | PLND | CLSD NCMP NMAT PRC | ZPM3 |  | 210 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-01-15 | 2013-01-15 | Y13WK03 | 10886740 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PRT NMAT PRC SETC | ZPM3 | 2UGM | 210 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-01-08 | 2013-01-08 | Y13WK02 | 10880119 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 210 | 210 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2013-01-01 | 2013-01-01 | Y13WK01 | 10873446 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PRT NMAT PRC SETC | ZPM3 | 2UGM | 210 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2012-12-25 | 2012-12-25 | Y12WK52 | 10866713 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PRT NMAT PRC SETC | ZPM3 | 2UGM | 140 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2012-12-18 | 2012-12-18 | Y12WK51 | 10859546 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PRT NMAT PRC SETC | ZPM3 | 2UGM | 210 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2012-12-11 | 2012-12-11 | Y12WK50 | 10852764 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF GMPS MACM PPRT PRC SETC | ZPM3 | 2UGM | 224.39 | 574.39 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2012-12-04 | 2012-12-04 | Y12WK49 | 10846276 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 210 | 140 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2012-11-27 | 2012-11-27 | Y12WK48 | 10839376 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 210 | 140 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2012-11-20 | 2012-11-22 | Y12WK47 | 10832680 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PRT NMAT PRC SETC | ZPM3 | 4UGM | 210 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2012-11-13 | 2012-11-13 | Y12WK46 | 10826297 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 210 | 225 | 30003897
100 |  |  |  |  | 2012-11-11 | 2012-11-12 | Y12WK45 | 10854983 | 10050BN267 | 267 | Bin, Headframe Surge | Repair Headframe lighting | TEMUEL | 02E | SCHD | CLSD PCNF ESTC GMPS MACM PPRT PRC SETC | ZPM1 | 7UGE | 981.84 | 701.92 | 30003859 | 10279356
310 | 426373 | 2031352 | 5023350 | 1 | 2012-11-06 | 2012-11-06 | Y12WK45 | 10819833 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 210 | 140 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2012-10-30 | 2012-10-30 | Y12WK44 | 10813617 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 210 | 70 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2012-10-23 | 2012-10-23 | Y12WK43 | 10806856 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PRT NMAT PRC SETC | ZPM3 | 2UGM | 210 | 0 | 30003897
200 | [5 empty] | 2012-10-17 |  | 10840742 | 10050BN267 | 267 | Bin, Headframe Surge | modify tipping scroll beam | TEMUME | 02M | APRD | CLSD PCNF ESTC NMAT PRC SETC | ZPM2 |  | 0 | 840 | 30003899 | 10274092
310 | 426373 | 2031352 | 5023350 | 1 | 2012-10-16 | 2012-10-16 | Y12WK42 | 10800152 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 210 | 210 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2012-10-09 | 2012-10-10 | Y12WK41 | 10793804 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 3UGM | 210 | 420 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2012-10-02 | 2012-10-02 | Y12WK40 | 10787652 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 210 | 140 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2012-09-25 | 2012-09-25 |  | 10781176 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | PLND | CLSD NCMP NMAT PRC | ZPM3 |  | 195 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2012-09-18 | 2012-09-18 | Y12WK38 | 10774154 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | PLND | CLSD PCNF PRT NMAT PRC SETC | ZPM3 | 2UGM | 195 | 65 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2012-09-11 | 2012-09-11 | Y12WK37 | 10767726 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PCNF GMPS MACM PPRT PRC SETC | ZPM3 | 2UGM | 498.31 | 498.31 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2012-09-04 | 2012-09-04 | Y12WK36 | 10760769 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | SCHD | CLSD PRT NMAT PRC SETC | ZPM3 | 2UGM | 195 | 0 | 30003897
310 | 426373 | 2031352 | 5023350 | 1 | 2012-08-28 | 2012-08-28 |  | 10754798 | 10050BN267 | 267 | Bin, Headframe Surge | SKIP DISCHARGE BIN WEEKLY INSP | TEMUME | 02M | PLND | CLSD NCMP NMAT PRC | ZPM3 |  | 195 | 0 | 30003897